## Read Me
Course Production Forecast
MeVn.ai ¦ Workforce Training Operations Planner
Forecast effort, cost, deadlines, and production risk for the learning pipeline.
STEP | WHAT TO DO | WORKBOOK CONTENTS
1 | Review the sample rows and replace them with your organization’s data. | 1. Production Forecast
2 | Use the dropdown fields to keep reporting consistent. | 2. Playbook & ROI Guide
3 | Enter or paste data only in input cells; calculated fields update automatically in Excel. | 3. Lists
4 | Use table filters and the KPI cards to focus on exceptions and priorities.
5 | Duplicate sample rows as needed and extend formulas/formatting for additional records.
6 | Adjust the blended hourly rate cell to reprice the whole pipeline instantly, then open the Playbook & ROI Guide sheet for the full plan-budget-schedule-track-implement-measure framework and a ready-to-use ROI calculator.
Template note: sample data is illustrative. Adapt categories, owners, dates, and policies to your organization. Validate all compliance requirements with the appropriate legal, regulatory, or internal policy owner.

## Production Forecast
Course Production Forecast
MeVn.ai • Plan workload, budgets, and launch readiness
COURSES |  | TOTAL HOURS |  | FORECAST COST |  | AT RISK |  |  | TRADITIONAL BLENDED PRODUCTION RATE ($/HR)
150
Course ID | Course Title | Sponsor | Priority | Complexity | Stage | Start Date | Launch Date | Est. Hours | Hours Complete | % Complete | Forecast Cost | Days to Launch | Risk | Owner | Est. Learners Reached | Budgeted Cost | Cost per Learner | Budget Variance | Target Runtime (min) | MeVn.ai Modules Equivalent
CRS-115 | Responsible AI Use | Legal | Critical | High | Review | 2026-06-15 | 2026-08-20 | 90 | 75 |  |  |  |  | Nora James | 850 | 16000 |  |  | 30
CRS-305 | Renewal Risk Analysis | Customer Success | High | Medium | Build | 2026-07-01 | 2026-10-01 | 60 | 31 |  |  |  |  | Amina Khan | 60 | 9500 |  |  | 30
CRS-520 | Coaching Conversations | Operations | High | Medium | Pilot | 2026-06-20 | 2026-09-20 | 60 | 48 |  |  |  |  | Priya Shah | 140 | 9000 |  |  | 30
CRS-720 | Accessible Content | Marketing | High | Medium | Design | 2026-07-10 | 2026-11-01 | 60 | 15 |  |  |  |  | Ethan Cole | 45 | 7500 |  |  | 30
CRS-910 | Data Privacy for Leaders | Privacy | Critical | High | Build | 2026-06-01 | 2026-08-10 | 135 | 89 |  |  |  |  | Rina Das | 90 | 18000 |  |  | 45
CRS-810 | Experiment Design | Product | Medium | High | Design | 2026-08-01 | 2026-12-01 | 135 | 18 |  |  |  |  | Maya Singh | 55 | 13000 |  |  | 45
CRS-630 | Finance Controls Refresher | Finance | Critical | Low | Intake | 2026-07-25 | 2026-09-01 | 24 | 0 |  |  |  |  | Wei Chen | 70 | 6000 |  |  | 20
CRS-330 | Advanced De-escalation | Support | Medium | Medium | Intake | 2026-08-10 | 2027-01-15 | 60 | 0 |  |  |  |  | Jamie Brooks | 65 | 9000 |  |  | 30
CRS-430 | Cloud Security Labs | Engineering | High | High | Build | 2026-05-15 | 2026-10-15 | 180 | 88 |  |  |  |  | Alex Morgan | 120 | 20000 |  |  | 60
CRS-220 | Strategic Negotiation | Sales | Medium | Medium | Design | 2026-08-05 | 2026-12-10 | 60 | 9 |  |  |  |  | Daniel Lee | 80 | 10500 |  |  | 30
CRS-530 | Performance Conversations | People | High | Medium | Review | 2026-06-25 | 2026-09-10 | 60 | 51 |  |  |  |  | Sofia Patel | 150 | 9500 |  |  | 30
CRS-120 | Ergonomics Essentials | Operations | Low | Low | Live | 2026-04-01 | 2026-07-01 | 24 | 24 |  |  |  |  | Priya Shah | 300 | 4500 |  |  | 20
Formulas:
Days to Launch = [Launch Date]-TODAY()

## Playbook & ROI Guide
L&D Manager Playbook
MeVn.ai • Plan, budget, schedule, track and prove the return on your production pipeline
Stage | What to do | How to go above and beyond
Plan | Prioritize the production backlog by business impact — Priority and Sponsor — not just by whichever course was requested first or is easiest to build. | Push back on Intake-stage requests that don't name a business sponsor and an audience size — a course with no accountable owner is the first one that stalls mid-Build.
Budget | Use the one-cell hourly rate toggle to reprice the entire pipeline instantly when your actual blended production rate changes — no need to re-enter 12 formulas by hand. | Track Budgeted Cost against Forecast Cost per course, not just in aggregate — the Budget Variance column shows you exactly which courses are quietly running over before the year-end review does.
Schedule | Watch Days to Launch alongside % Complete — a course at 20% complete with 30 days to launch is a very different risk than one at 80% complete with 30 days left. | Re-sequence Design-stage courses around Build-stage courses that are close to done — finishing what's nearly complete protects launch dates better than starting everything at once.
Track | Let the Risk formula do the flagging for you — it already combines days remaining and percent complete so you don't have to eyeball every row every week. | Review Cost per Learner Reached alongside Risk — a course that's on schedule but reaches very few learners may be a lower priority than a slightly-at-risk course reaching hundreds.
Implement | Update Hours Complete weekly, not just at each stage change — % Complete is only as trustworthy as how often it's refreshed. | Hold a short review the moment a course flips to “At Risk” — catching a slip in week one is far cheaper than catching it two weeks from launch.
Measure Impact & ROI | Use Est. Learners Reached and Forecast Cost together — Cost per Learner Reached tells you which courses deliver the most capability per dollar spent, which is a better production-priority signal than cost alone. | Use the ROI calculator below to show leadership the return on the whole pipeline, not just its cost — a budget conversation framed around value lands very differently than one framed only around spend.
ROI Calculator
Blue cells are auto-calculated from the Production Forecast. Yellow cells are your inputs — replace the sample figures with your own before you rely on the result.
Total forecast production cost, all courses (auto, from Production Forecast)
Total learners reached, all courses (auto)
Estimated value delivered per learner reached — e.g. faster ramp, fewer errors, avoided rework (YOUR INPUT) |  | 60
Estimated total value delivered
Production ROI
Estimated return per $1 invested
This calculator estimates value from the sample per-learner assumption above — it is a planning tool, not an audited financial figure. Replace the yellow input with your organization's own numbers before presenting this to Finance or leadership.
What This Pipeline Would Cost With MeVn.ai
The Forecast Cost column above uses a traditional blended production rate (in-house team or agency). Compare that to what the same pipeline costs on MeVn.ai's standard production rate.
Total forecast cost at the traditional blended rate (auto, from above)
MeVn.ai modules equivalent, this pipeline (auto — by learner-minutes, not course count)
MeVn.ai standard rate, per 30-minute module (YOUR INPUT — $3,500/module on the Production plan, or $5,000 one-time via the Course Pilot) |  | 3500
Equivalent cost for this pipeline on MeVn.ai
Estimated savings with MeVn.ai ($)
Estimated savings with MeVn.ai (%)
The traditional rate above is an editable planning assumption (default: $150/hr blended instructional design, development and review), not a universal industry figure — adjust it to match your own team's or vendor's real cost. Want to test MeVn.ai directly? The one-time $5,000 Course Pilot delivers one complete module in 10 business days, no subscription required.

## Lists
Priority | Stage | Complexity
Critical | Intake | Low
High | Design | Medium
Medium | Build | High
Low | Review
Pilot
Live